## Sheet1
Task ID | Task Typ | Task Name | Priority | Predecessors(Task ID) | Complete% | Duration(day) | daysPast | daysRemain | Start Date | Finish Date | Resource Name | delivery | Status | Details | today
1 | grand | General Computing | high |  | 7.684% | 475 | 103 | 372 | 2022-01-01 | 2023-04-21 | Gene |  | ACTIVE |  | 2022-04-14
2 | parent | ARCH Specification | high |  | 7.273% | 330 | 103 | 227 | 2022-01-01 | 2022-11-27 | Gene | doc | ACTIVE
3 | child | Fused Scalar Shader ISA SPEC | high |  | 10% | 120 | 103 | 17 | 2022-01-01 | 2022-05-01 | Gene | doc | ACTIVE
4 | child | FSP SPEC | high |  | 10% | 120 | 103 | 17 | 2022-01-01 | 2022-05-01 | Gene | doc | ACTIVE
5 | child | MP SPEC | high |  | 0% | 30 | 44 | 0 | 2022-03-01 | 2022-03-31 | Gene | doc | ACTIVE
6 | child | WD(CWD) SPEC | high | 5 | 0% | 30 | 0 | 47 | 2022-05-01 | 2022-05-31 | Gene | doc | ACTIVE
7 | child | MPC SPEC | high | 6 | 0% | 30 | 0 | 77 | 2022-05-31 | 2022-06-30 | Gene | doc | ACTIVE
8 | parent | ARCH Modeling | low |  | 10% | 125 | 44665 | 0 |  | 1900-05-04 | Gene | doc,code | STALL
9 | child | Highest Level Analytical Performance Model (PMDL) | low |  | 10% | 20 | 44665 | 0 |  | 1900-01-19 | Gene | doc,code | STALL
10 | child | Highest Level Analytical Energe Model (EMDL) | low | 9 | 0% | 20 |  | 0 |  | 1900-01-19 |  |  | STALL
11 | child | Highly Abstracted Algorithm Model/Emulator (SMDL) | low |  | 50% | 5 | 72 | 0 | 2022-02-01 | 2022-02-06 | Gene | code | STALL
12 | child | Algorithm Implementation Functional Model (CMDL) | low |  | 10% | 20 | 44665 | 0 |  | 1900-01-19 | Gene | code | STALL
13 | child | Architecture/Microarchitecture Cycle Model (AMDL) | low |  | 10% | 40 | 44665 | 0 |  | 1900-02-08 | Gene | code | STALL
14 | child | HLS Flow for Verilog Model (VMDL) | low |  | 10% | 20 | 44665 | 0 |  | 1900-01-19 | Gene | doc,code | STALL
15 | parent | EDA Flow for Power and Area Estimation | low |  | 0% | 20 | 44665 | 0 |  |  | Gene | code | STALL
16 | grand | Memory Model | middle |  | 10.77% | 65 | 72 | 0 | 2022-02-01 | 2022-04-07 | Gene |  | ACTIVE
17 | child | WRL-95-7 | middle |  | 100% | 5 | 72 | 0 | 2022-02-01 | 2022-02-06 | Gene | note | ACTIVE
18 | child | WRL-95-9 | middle |  | 10% | 20 | 66 | 0 | 2022-02-07 | 2022-02-27 | Gene |  | STALL
19 | child | volta-memory model | middle |  | 0% | 20 | 45 | 0 | 2022-02-28 | 2022-03-20 | Gene |  | STALL
20 | child | memory model ISA support | middle |  | 0% | 20 | 24 | 0 | 2022-03-21 | 2022-04-10 | Gene |  | STALL
21 | child | Fused Scalar Shader ISA SPEC, Memory Model Section | middle |  | 0% | 20 | 3 | 17 | 2022-04-11 | 2022-05-01 | Gene |  | STALL
22 | grand | Deep Learning | high |  | 55% | 85 | 35 | 50 | 2022-03-10 | 2022-06-03 | Gene |  | ACTIVE
23 | child | Deep Learning for Compute Architects | high |  | 30% | 30 | 35 | 0 | 2022-03-10 | 2022-04-09 | Gene | note | ACTIVE
24 | child | Standford DL/ML Class | high |  | 10% | 20 | 30 | 0 | 2022-03-15 | 2022-04-04 | Gene | note | PEND
25 | parent | NVDLA Bring up | high | 23 | 0% | 35 | 4 | 31 | 2022-04-10 | 2022-05-15 | Gene | doc,code | PEND
26 | child | NVDLA1.0 | high | 23 | 0% | 5 | 4 | 1 | 2022-04-10 | 2022-04-15 | Gene | note | PEND
27 | child | NVDLA2.0 | high | 26 | 0% | 5 | 5 | 0 | 2022-04-09 | 2022-04-14 | Gene |  | PEND
28 | child | NVDLA3.0 | high | 27 | 0% | 5 | 10 | 0 | 2022-04-04 | 2022-04-09 | Gene |  | PEND
29 | child | Integrate NVDLA into CGL21080 | high | 28 | 0% | 20 | 0 | 51 | 2022-05-15 | 2022-06-04 | Gene | code | STALL
30 | grand | Compute Graphics | low |  | 6.667% | 90 | 44665 | 0 |  | 1900-03-30 | Gene |  | STALL
31 | child | GAMES101 Class | low |  | 10% | 20 | 44665 | 0 |  | 1900-01-19 | Gene | note | STALL
32 | child | Ray Tracing | low |  | 0% | 10 | 44665 | 0 |  | 1900-01-09 | Gene |  | STALL
33 | child | D3D12 study | low |  | 10% | 40 | 44665 | 0 |  | 1900-02-08 | Gene |  | STALL
34 | child | WD(GWD) Spec | low |  | 0% | 10 | 44665 | 0 |  | 1900-01-09 | Gene |  | STALL
35 | child | GPM Spec | low |  | 0% | 10 | 44665 | 0 |  | 1900-01-09 | Gene |  | STALL
36 | grand | Tool Development | low |  | 18.89% | 45 | 44665 | 0 |  | 1900-02-13 | Gene |  | STALL
37 | parent | Compute/Graphics Execution Trace Data Structure | low |  | 10% | 5 | 44665 | 0 |  | 1900-01-04 | Gene | doc,code | STALL
38 | parent | Profiling Data Structure and Driver Support | low |  | 10% | 10 | 44665 | 0 |  | 1900-01-09 | Gene | code | STALL
39 | child | GPUVis Data Visualization Tool Porting | low | 37 | 10% | 10 | 44665 | 0 |  | 1900-01-09 | Gene | doc,code | STALL
40 | parent | API Trace/Playback System | low |  | 40% | 10 | 44665 | 0 |  | 1900-01-09 | Gene | doc,code | STALL
41 | parent | HAL Trace, Testbench playback system | low | 15 | 20% | 10 | 44665 | 0 |  | 1900-01-09 | Gene | doc,code | STALL
| child | R Language Study | high |  | 0%
Formulas:
Finish Date = [Start Date]+[Duration(day)]
Start Date = [Start Date, row above]
Start Date = INDIRECT(ADDRESS([Predecessors(Task ID)]-1,COLUMN()+1))