## Schedule
Task ID | Task Hierarchy | Task Name | Priority | Predecessors(Task ID) | Complete% | Duration(day) | daysPast | daysRemain | Start Date | Finish Date | Resource Name | delivery | Status | Details | today
1 | grand | General Computing | middle |  | 13.29% | 365 | 123 | 242 | 2022-01-01 | 2023-01-01 | Gene |  | ACTIVE |  | 2022-05-04
2 | parent | ARCH Specification | middle |  | 15% | 240 | 123 | 117 | 2022-01-01 | 2022-08-29 | Gene | doc | ACTIVE
3 | child | Fused Scalar Shader ISA SPEC | high |  | 20% | 120 | 123 | 0 | 2022-01-01 | 2022-05-01 | Gene | doc | ACTIVE
4 | child | FSP/MP/WD(CWD/GWD)MPC SPEC | high |  | 10% | 120 | 123 | 0 | 2022-01-01 | 2022-05-01 | Gene | doc | ACTIVE
5 | parent | Highest Level Analytical Performance Model (PMDL) | low |  | 10% | 20 | 44685 | 0 |  | 1900-01-19 | Gene | doc,code | STALL
6 | parent | Highly Abstracted Algorithm Model/Emulator (SMDL) | low |  | 50% | 5 | 92 | 0 | 2022-02-01 | 2022-02-06 | Gene | code | STALL
7 | parent | Algorithm Implementation Functional Model (CMDL) | low |  | 10% | 20 | 44685 | 0 |  | 1900-01-19 | Gene | code | STALL
8 | parent | Architecture/Microarchitecture Cycle Model (AMDL) | low | 14 | 10% | 40 | 44685 | 0 |  | 1900-02-08 | Gene | code | STALL
9 | parent | HLS Flow for Verilog Model (VMDL) | low |  | 10% | 20 | 44685 | 0 |  | 1900-01-19 | Gene | doc,code | STALL
10 | child | integrate matchlib int CG1 | middle |  | 10% | 10 |  | 0 |  | 1900-01-09 |  |  | PEND
11 | parent | EDA Flow for Power and Area Estimation | low |  | 0% | 20 | 44685 | 0 |  |  | Gene | code | STALL
12 | grand | Memory Model | middle |  | 6.667% | 45 | 92 | 0 | 2022-02-01 | 2022-03-18 | Gene |  | ACTIVE
13 | child | Papers Note | middle |  | 60% | 5 | 92 | 0 | 2022-02-01 | 2022-02-06 | Gene | note | ACTIVE
14 | child | volta-memory model | middle |  | 0% | 20 | #REF! | #REF! | #REF! | #REF! | Gene |  | STALL
15 | child | memory model ISA support | middle |  | 0% | 20 | #REF! | #REF! | #REF! | #REF! | Gene |  | STALL
16 | child | Fused Scalar Shader ISA SPEC, Memory Model Section | middle |  | 50% | 20 | #REF! | #REF! | #REF! | #REF! | Gene |  | ACTIVE
17 | grand | Compute Graphics | low |  | 15% | 100 | 44685 | 0 |  | 1900-04-09 | Gene |  | STALL
18 | child | GAMES101 Class | low |  | 10% | 20 | 44685 | 0 |  | 1900-01-19 | Gene | note | STALL
19 | child | D3D12 study(Ray Tracing) | low |  | 10% | 40 | 44685 | 0 |  | 1900-02-08 | Gene |  | STALL
20 | child | CG1 environment setup | middle |  | 30% | 30 |  | 0 |  | 1900-01-29
21 | child | GPM/WD(GWD)/RT SPEC | low |  | 0% | 10 | 44685 | 0 |  | 1900-01-09 | Gene |  | STALL
22 | grand | Deep Learning | middle |  | 60.71% | 70 | 55 | 15 | 2022-03-10 | 2022-05-19 | Gene |  | ACTIVE
23 | child | Deep Learning for Compute Architects | high |  | 90% | 45 | 55 | 0 | 2022-03-10 | 2022-04-24 | Gene | note | ACTIVE
24 | child | Standford/Taiwan DL/ML Class | high |  | 10% | 20 | 50 | 0 | 2022-03-15 | 2022-04-04 | Gene | note | PEND
25 | parent | NVDLA Bring up | middle | 23 | 0% | 5 | 44655 | 0 | 1900-01-29 | 1900-02-03 | Gene | doc,code | PEND
26 | child | NVDLA1.0/2.0/3.0 CG2 setup | middle | 23 | 0% | 5 | 44655 | 0 | 1900-01-29 | 1900-02-03 | Gene | note | PEND
27 | grand | Tool Development | low |  | 18.89% | 45 | 44685 | 0 |  | 1900-02-13 | Gene |  | STALL
28 | parent | Compute/Graphics Execution Trace Data Structure | low |  | 10% | 5 | 44685 | 0 |  | 1900-01-04 | Gene | doc,code | STALL
29 | parent | Profiling Data Structure and Driver Support | low |  | 10% | 10 | 44685 | 0 |  | 1900-01-09 | Gene | code | STALL
30 | child | GPUVis Data Visualization Tool Porting | low | 28 | 10% | 10 | 44685 | 0 |  | 1900-01-09 | Gene | doc,code | STALL
31 | parent | API Trace/Playback System | low |  | 40% | 10 | 44685 | 0 |  | 1900-01-09 | Gene | doc,code | STALL
32 | parent | HAL Trace, Testbench playback system | low | 11 | 20% | 10 | 44685 | 0 |  | 1900-01-09 | Gene | doc,code | STALL
33 | child | R Language Study | high |  | 0% | 30 |  | 0 |  | 30 |  |  | ACTIVE
Formulas:
Finish Date = [Start Date]+[Duration(day)]
Start Date = [Start Date, row above]
Start Date = INDIRECT(ADDRESS([Predecessors(Task ID)]-2,COLUMN()+1))